## 📊 Dashboard
CyberAssetIQ – User Acceptance Test Tracker
TotalIT Solutions Limited ¦ Company No. 16537549
Tester Name: | Wole Jimlas Adekola |  | Test Environment: | Docker ¦ FastAPI ¦ PostgreSQL 16
Start Date: |  |  | Backend URL: | http://192.168.0.179:8000
End Date: |  |  | Agent Machine: | 192.168.0.149 (port 8099)
Version: | v2.4+ |  | API Key: | cyberassetiq-admin-key-001
Tenant: | tenant-001 |  | Container: | cyberassetiq-backend-1
MODULE | TOTAL TESTS | PASSED ✅ | FAILED ❌ | SKIPPED ⏭ | PENDING ⏳ | PASS RATE
01 – Authentication & User Management
02 – Asset Discovery & Inventory
03 – Windows Agent
04 – Network Discovery
05 – Vulnerability Management
06 – Credential / Secret Leak Detection
07 – Dark Web Exposure
08 – Cyber Essentials v3.2 Compliance
09 – AI Security Intelligence
10 – SIEM & EDR Integrations
11 – IAM Integrations (Entra / Okta)
12 – ITSM & MSP Integrations
13 – Reporting & Evidence Packages
14 – Multi-Tenancy & RBAC
15 – Notifications & Alerts
16 – API Endpoints
17 – Dashboard UI & UX
TOTAL
LEGEND
Passed | Feature works correctly end-to-end (browser + API verified)
Failed | Feature did not work – use Comments column to describe issue
Skipped | Not tested in this cycle (dependency or environment issue)
Pending | Not yet tested – still to do

## 01 Auth
CyberAssetIQ – Module 01 – Authentication & User Management
Test Status: Pending ¦ Fill in columns E–H for each test case
TEST ID | TEST NAME | TEST STEPS / HOW TO TEST | EXPECTED RESULT | STATUS | DATE TESTED | TESTER NOTES / BUG DESCRIPTION | PRIORITY
AUTH-01 | Admin Login via UI | 1. Open http://192.168.0.179:8000 2. Enter admin credentials 3. Click Login | Redirected to main dashboard. Session token issued. No errors. | Pending |  |  | High
AUTH-02 | API Key Authentication | 1. Call GET /api/v1/assets with header X-API-Key: cyberassetiq-admin-key-001 2. Verify 200 response | 200 OK response with asset data returned | Pending |  |  | High
AUTH-03 | Invalid API Key Rejected | 1. Call GET /api/v1/assets with header X-API-Key: invalid-key 2. Check response code | 401 Unauthorized response | Pending |  |  | High
AUTH-04 | Token Expiry & Refresh | 1. Log in 2. Wait for session expiry or manually expire token 3. Attempt API call | 401 returned with message to re-authenticate. No stale session. | Pending |  |  | Medium
AUTH-05 | Multi-User Login (tenant-001) | 1. Create a second user under tenant-001 2. Log in with new user 3. Verify data isolation | New user can log in. Sees only their tenant data. | Pending |  |  | High
AUTH-06 | Password Reset Flow | 1. Click 'Forgot Password' 2. Enter registered email 3. Follow reset link | Reset email sent. Password updated. User can log in with new password. | Pending |  |  | Medium
AUTH-07 | Logout Clears Session | 1. Log in 2. Click Logout 3. Try to navigate to a protected page | Session invalidated. Redirected to login page. API returns 401. | Pending |  |  | Medium
💡 HOW TO USE: Select STATUS dropdown → choose Passed / Failed / Skipped. For Failed tests, describe the exact error in the TESTER NOTES column. Date format: DD/MM/YYYY

## 02 Assets
CyberAssetIQ – Module 02 – Asset Discovery & Inventory
Test Status: Pending ¦ Fill in columns E–H for each test case
TEST ID | TEST NAME | TEST STEPS / HOW TO TEST | EXPECTED RESULT | STATUS | DATE TESTED | TESTER NOTES / BUG DESCRIPTION | PRIORITY
ASSET-01 | Asset List Loads | 1. Log in 2. Navigate to Assets section 3. Observe asset list | Asset table loads with columns: name, IP, OS, last seen, risk score. | Pending |  |  | High
ASSET-02 | Manual Asset Creation | 1. Click 'Add Asset' 2. Fill in name, IP, OS type 3. Save | New asset appears in list immediately. Stored in DB. | Pending |  |  | High
ASSET-03 | Asset Search & Filter | 1. In asset list, type a hostname in the search box 2. Apply OS filter | Filtered results match search term. Non-matching assets hidden. | Pending |  |  | Medium
ASSET-04 | Asset Detail View | 1. Click any asset in the list 2. View detail panel | Detail panel shows: IP, MAC, OS, patch level, open CVEs, last scan time. | Pending |  |  | High
ASSET-05 | Asset Deduplication | 1. Submit the same asset twice (same MAC/IP) 2. Check asset count | Only one entry created. Canonical merge logic prevents duplicate. | Pending |  |  | High
ASSET-06 | Asset Edit & Update | 1. Open an existing asset 2. Edit the hostname 3. Save | Updated hostname reflected immediately. Audit log entry created. | Pending |  |  | Medium
ASSET-07 | Asset Delete | 1. Select an asset 2. Click Delete 3. Confirm | Asset removed from list. Not retrievable via API. | Pending |  |  | Low
ASSET-08 | Asset Risk Score Display | 1. View an asset with known CVEs 2. Check risk score | Risk score is calculated and displayed. High CVE count = High risk. | Pending |  |  | High
ASSET-09 | Cloud Asset Discovery (Azure/AWS) | 1. Configure cloud integration credentials 2. Trigger cloud scan | Cloud resources appear as assets with provider tag (Azure/AWS). | Pending |  |  | High
ASSET-10 | SaaS Asset Discovery | 1. Connect an Office 365 / Google Workspace account 2. Run discovery | SaaS services appear as assets in inventory. | Pending |  |  | Medium
💡 HOW TO USE: Select STATUS dropdown → choose Passed / Failed / Skipped. For Failed tests, describe the exact error in the TESTER NOTES column. Date format: DD/MM/YYYY

## 03 Agent
CyberAssetIQ – Module 03 – Windows Agent
Test Status: Pending ¦ Fill in columns E–H for each test case
TEST ID | TEST NAME | TEST STEPS / HOW TO TEST | EXPECTED RESULT | STATUS | DATE TESTED | TESTER NOTES / BUG DESCRIPTION | PRIORITY
AGENT-01 | Agent Registers with Backend | 1. On 192.168.0.149, start Windows agent 2. Check http://192.168.0.179:8000/api/v1/agents | Agent appears with status 'active', IP, hostname visible. | Pending |  |  | High
AGENT-02 | Agent Heartbeat | 1. Leave agent running for 5 minutes 2. Check last_seen timestamp in agent list | last_seen updates every heartbeat interval (≤5 min). | Pending |  |  | High
AGENT-03 | Agent Collects Endpoints | 1. After agent runs discovery 2. Check asset list for new entries from agent machine | Endpoints discovered by agent appear in asset inventory. | Pending |  |  | High
AGENT-04 | Registry Scan | 1. Agent performs registry scan 2. Check assets for installed software list | Installed software populated against the asset from registry data. | Pending |  |  | High
AGENT-05 | Agent Offline Detection | 1. Stop the agent service 2. Wait 10+ minutes 3. Check agent status | Agent status changes to 'inactive' or 'offline'. Alert triggered. | Pending |  |  | Medium
AGENT-06 | Agent Auto-Reconnect | 1. Stop agent, wait 5 minutes, restart 2. Check backend | Agent reconnects and resumes data posting without manual intervention. | Pending |  |  | Medium
AGENT-07 | Agent Reports Patch Level | 1. Run agent on a Windows machine with known missing patches 2. Check vulnerability data | Missing patches listed under the asset in vulnerability module. | Pending |  |  | High
💡 HOW TO USE: Select STATUS dropdown → choose Passed / Failed / Skipped. For Failed tests, describe the exact error in the TESTER NOTES column. Date format: DD/MM/YYYY

## 04 Network
CyberAssetIQ – Module 04 – Network Discovery
Test Status: Pending ¦ Fill in columns E–H for each test case
TEST ID | TEST NAME | TEST STEPS / HOW TO TEST | EXPECTED RESULT | STATUS | DATE TESTED | TESTER NOTES / BUG DESCRIPTION | PRIORITY
NET-01 | Network Scan Initiation | 1. Go to Network Discovery 2. Enter subnet (e.g. 192.168.0.0/24) 3. Click Scan | Scan starts. Progress indicator shown. Assets discovered. | Pending |  |  | High
NET-02 | Discovered Assets Added to Inventory | 1. After network scan completes 2. Check asset list | All discovered hosts added to inventory with IP, MAC, open ports. | Pending |  |  | High
NET-03 | Port Scan Results | 1. Run scan on a known host 2. View port results | Open ports listed correctly (e.g. 80, 443, 3389 where applicable). | Pending |  |  | High
NET-04 | Scan History | 1. Run two scans on same subnet 2. Check scan history | Both scans listed with timestamps. Delta changes highlighted. | Pending |  |  | Medium
NET-05 | Agentless Discovery (No agent installed) | 1. Target a machine with no agent 2. Run network scan | Machine discovered via network scan and added to inventory. | Pending |  |  | High
💡 HOW TO USE: Select STATUS dropdown → choose Passed / Failed / Skipped. For Failed tests, describe the exact error in the TESTER NOTES column. Date format: DD/MM/YYYY

## 05 Vulns
CyberAssetIQ – Module 05 – Vulnerability Management
Test Status: Pending ¦ Fill in columns E–H for each test case
TEST ID | TEST NAME | TEST STEPS / HOW TO TEST | EXPECTED RESULT | STATUS | DATE TESTED | TESTER NOTES / BUG DESCRIPTION | PRIORITY
VULN-01 | CVE List Loads for Asset | 1. Open an asset detail 2. Navigate to Vulnerabilities tab | CVEs listed with: CVE ID, CVSS score, severity, description, patch status. | Pending |  |  | High
VULN-02 | NVD API Integration | 1. Trigger vulnerability sync 2. Check CVE data is from NVD | CVEs correlate to NVD data. Descriptions match NVD records. | Pending |  |  | High
VULN-03 | Vulnerability Severity Filter | 1. In vuln list, filter by 'Critical' 2. Verify only critical CVEs shown | Only CVSS 9.0+ CVEs displayed when Critical filter applied. | Pending |  |  | Medium
VULN-04 | Mark as Accepted Risk | 1. Select a CVE on an asset 2. Click 'Accept Risk' 3. Add justification 4. Save | CVE marked as Accepted Risk. Suppressed from active findings. Permanent. | Pending |  |  | High
VULN-05 | Mark as False Positive | 1. Select a CVE 2. Click 'False Positive' 3. Add reason 4. Save | CVE suppressed from active findings. Permanent flag. Not re-opened on rescan. | Pending |  |  | High
VULN-06 | Mark as Resolved | 1. Apply a patch to a test asset 2. Rescan 3. Check CVE status | CVE moves to Resolved. If patch removed and rescanned, CVE re-opens. | Pending |  |  | High
VULN-07 | Vulnerability Dashboard Summary | 1. Go to Vulnerability Dashboard 2. Check summary counts | Counts for Critical/High/Medium/Low match total CVEs across all assets. | Pending |  |  | Medium
VULN-08 | Patch Compliance Dashboard | 1. Navigate to Patch Tracker 2. Check missing patches list | Missing patches listed by asset. Percentage compliance score shown. | Pending |  |  | High
VULN-09 | Vulnerability Scan as Immutable Snapshot | 1. Run scan 2. Note CVE count 3. Run second scan 4. Verify both snapshots retained | Each scan stored as a separate immutable snapshot. No upsert. Both visible. | Pending |  |  | High
💡 HOW TO USE: Select STATUS dropdown → choose Passed / Failed / Skipped. For Failed tests, describe the exact error in the TESTER NOTES column. Date format: DD/MM/YYYY

## 06 Secrets
CyberAssetIQ – Module 06 – Credential / Secret Leak Detection
Test Status: Pending ¦ Fill in columns E–H for each test case
TEST ID | TEST NAME | TEST STEPS / HOW TO TEST | EXPECTED RESULT | STATUS | DATE TESTED | TESTER NOTES / BUG DESCRIPTION | PRIORITY
SEC-01 | Secret Scan UI Initiates | 1. Navigate to Secret/Credential Detection 2. Click Run Scan | Scan starts. Progress shown. | Pending |  |  | High
SEC-02 | API Key Pattern Detection | 1. Place a dummy AWS key format string in a test file 2. Run scan | AWS key detected. Shown in results with file path, line, entropy score. | Pending |  |  | High
SEC-03 | SecretScore ML Confidence Score | 1. View scan results 2. Check each finding for confidence score | Each finding shows a SecretScore (0–100). High entropy = High score. | Pending |  |  | High
SEC-04 | False Positive Reduction | 1. Scan a file with a commented-out/example API key 2. Check score | Commented/example keys score lower than real credentials (≤50%). | Pending |  |  | High
SEC-05 | Dark Web Match Flag | 1. If a found secret matches a dark web record 2. Check flag in results | Finding flagged with 'Dark Web Match' indicator and source reference. | Pending |  |  | Medium
SEC-06 | Secret Finding Suppression | 1. Mark a finding as False Positive 2. Re-run scan | Suppressed finding does not reappear in new scan results. | Pending |  |  | High
SEC-07 | 23-Feature Logistic Regression (SecretScore) | 1. Review the feature breakdown on a finding 2. Check features used | Features visible: entropy, file type, context, proximity to API calls etc. | Pending |  |  | Medium
SEC-08 | GitHub Repository Scan | 1. Connect a GitHub repo 2. Run secret scan on repo | Repo scanned. Secrets in commit history and current code detected. | Pending |  |  | Medium
💡 HOW TO USE: Select STATUS dropdown → choose Passed / Failed / Skipped. For Failed tests, describe the exact error in the TESTER NOTES column. Date format: DD/MM/YYYY

## 07 DarkWeb
CyberAssetIQ – Module 07 – Dark Web Exposure
Test Status: Pending ¦ Fill in columns E–H for each test case
TEST ID | TEST NAME | TEST STEPS / HOW TO TEST | EXPECTED RESULT | STATUS | DATE TESTED | TESTER NOTES / BUG DESCRIPTION | PRIORITY
DW-01 | Dark Web Module Loads | 1. Navigate to Dark Web Exposure module 2. Check page loads | Module page loads. No errors. Status shows last scan time. | Pending |  |  | Medium
DW-02 | Domain Exposure Check | 1. Enter company domain 2. Run exposure check | Results show any exposed credentials matching the domain on dark web sources. | Pending |  |  | High
DW-03 | Email Exposure Check | 1. Enter a business email 2. Run check | Any breached records for that email shown with breach source name and date. | Pending |  |  | High
DW-04 | Exposure Alert Trigger | 1. Confirm an email that has known breach data 2. Check alerts | Alert triggered in Notifications for the exposed email. | Pending |  |  | High
DW-05 | Historical Exposure Records | 1. Run two checks over time 2. View history | Both check results stored with timestamps. Trend visible. | Pending |  |  | Low
💡 HOW TO USE: Select STATUS dropdown → choose Passed / Failed / Skipped. For Failed tests, describe the exact error in the TESTER NOTES column. Date format: DD/MM/YYYY

## 08 CE
CyberAssetIQ – Module 08 – Cyber Essentials v3.2 Compliance
Test Status: Pending ¦ Fill in columns E–H for each test case
TEST ID | TEST NAME | TEST STEPS / HOW TO TEST | EXPECTED RESULT | STATUS | DATE TESTED | TESTER NOTES / BUG DESCRIPTION | PRIORITY
CE-01 | CE v3.2 Dashboard Loads | 1. Navigate to Cyber Essentials module 2. Check control status summary | Dashboard shows all CE controls (A1–A8) with pass/partial/fail status. | Pending |  |  | High
CE-02 | A1 Asset Register – Auto-Populated | 1. After running asset discovery 2. Check CE A1 control | Asset register automatically populated from discovered assets. | Pending |  |  | High
CE-03 | A2 User Access Control | 1. Run identity scan 2. Check CE A2 control | User list with admin accounts identified. Permissions matrix visible. | Pending |  |  | High
CE-04 | A3 Secure Configuration Check | 1. Run configuration audit on an asset 2. Check CE A3 status | Baseline comparison report generated. Deviations flagged. | Pending |  |  | High
CE-05 | A4 Vulnerability Management | 1. Ensure vulnerability scan is complete 2. Check CE A4 status | Scan report auto-mapped to CE A4. Patch status shown. | Pending |  |  | High
CE-06 | A5 Patch Management | 1. Check patch compliance dashboard 2. Review CE A5 status | Missing patches listed. Patch compliance % shown for CE A5. | Pending |  |  | High
CE-07 | Evidence Package Generation | 1. Click 'Generate CE Evidence Package' 2. Download PDF | PDF generated with all CE controls, evidence, asset data, and timestamps. | Pending |  |  | High
CE-08 | Non-Compliant Asset Remediation Guidance | 1. Find a non-compliant asset in CE view 2. Click on it | Remediation steps shown for the specific non-compliance. | Pending |  |  | Medium
CE-09 | CE Readiness Score | 1. View CE dashboard 2. Check overall readiness score | Score (%) shows percentage of CE controls passing. Updates live. | Pending |  |  | Medium
💡 HOW TO USE: Select STATUS dropdown → choose Passed / Failed / Skipped. For Failed tests, describe the exact error in the TESTER NOTES column. Date format: DD/MM/YYYY

## 09 AI
CyberAssetIQ – Module 09 – AI Security Intelligence
Test Status: Pending ¦ Fill in columns E–H for each test case
TEST ID | TEST NAME | TEST STEPS / HOW TO TEST | EXPECTED RESULT | STATUS | DATE TESTED | TESTER NOTES / BUG DESCRIPTION | PRIORITY
AI-01 | AI Security Intelligence Module Loads | 1. Navigate to AI Security Intelligence 2. Check page loads | Module loads without errors. AI provider shown (Groq/Gemini/Anthropic/OpenAI). | Pending |  |  | High
AI-02 | AI Threat Summary for Asset | 1. Open an asset with CVEs 2. Request AI threat summary | AI generates a natural-language threat summary for the asset. | Pending |  |  | High
AI-03 | AI Fallback Chain (Groq → Gemini → Anthropic → OpenAI) | 1. Disable Groq API key 2. Trigger AI query 3. Verify fallback provider used | AI query answered by next provider in chain. No error shown to user. | Pending |  |  | High
AI-04 | Natural Language Asset Query | 1. Type 'Show me all Windows assets with Critical CVEs' 2. Submit | Correct filtered asset list returned based on natural language query. | Pending |  |  | Medium
AI-05 | AI Remediation Recommendations | 1. Select a Critical CVE 2. Request AI remediation advice | AI provides specific, actionable remediation steps for that CVE. | Pending |  |  | High
AI-06 | AI Dark Web Insight | 1. View a dark web exposure finding 2. Request AI analysis | AI explains the exposure context, likely impact, and recommended actions. | Pending |  |  | Medium
💡 HOW TO USE: Select STATUS dropdown → choose Passed / Failed / Skipped. For Failed tests, describe the exact error in the TESTER NOTES column. Date format: DD/MM/YYYY

## 10 SIEM-EDR
CyberAssetIQ – Module 10 – SIEM & EDR Integrations
Test Status: Pending ¦ Fill in columns E–H for each test case
TEST ID | TEST NAME | TEST STEPS / HOW TO TEST | EXPECTED RESULT | STATUS | DATE TESTED | TESTER NOTES / BUG DESCRIPTION | PRIORITY
INT-01 | Sentinel Integration Connect | 1. Navigate to Integrations → SIEM → Sentinel 2. Enter credentials 3. Save & Test | Connection successful. Green status badge shown. | Pending |  |  | High
INT-02 | Splunk Integration Connect | 1. Navigate to Integrations → SIEM → Splunk 2. Enter HEC URL & token 3. Test | Events forwarded to Splunk. Test event visible in Splunk. | Pending |  |  | High
INT-03 | CrowdStrike EDR Connect | 1. Navigate to Integrations → EDR → CrowdStrike 2. Enter API credentials 3. Test | Connection established. EDR asset data synced. | Pending |  |  | High
INT-04 | Microsoft Defender Connect | 1. Navigate to Integrations → EDR → Defender 2. Enter tenant/app credentials 3. Test | Defender alerts visible in CyberAssetIQ findings. | Pending |  |  | High
INT-05 | Dispatcher Routes Events | 1. Trigger a security event (e.g. critical CVE found) 2. Check all active integrations | Event dispatched to all connected integrations simultaneously. | Pending |  |  | High
INT-06 | Integration Health Dashboard | 1. Navigate to Integrations overview 2. Check health status | All integrations show: status, last sync time, event count. | Pending |  |  | Medium
💡 HOW TO USE: Select STATUS dropdown → choose Passed / Failed / Skipped. For Failed tests, describe the exact error in the TESTER NOTES column. Date format: DD/MM/YYYY

## 11 IAM
CyberAssetIQ – Module 11 – IAM Integrations
Test Status: Pending ¦ Fill in columns E–H for each test case
TEST ID | TEST NAME | TEST STEPS / HOW TO TEST | EXPECTED RESULT | STATUS | DATE TESTED | TESTER NOTES / BUG DESCRIPTION | PRIORITY
IAM-01 | Entra ID (Azure AD) Connect | 1. Navigate to Integrations → IAM → Entra ID 2. Enter tenant ID, client ID, secret 3. Test | Connection successful. User list synced from Entra. | Pending |  |  | High
IAM-02 | Okta Connect | 1. Navigate to Integrations → IAM → Okta 2. Enter domain & API token 3. Test | Connection successful. Okta user/group data synced. | Pending |  |  | High
IAM-03 | Privileged Account Detection | 1. After IAM sync 2. Check Identity Scanner results | Admin/privileged accounts flagged. List matches actual Entra/Okta admin list. | Pending |  |  | High
IAM-04 | Stale Account Detection | 1. In IAM sync results 2. Check for accounts with no recent login | Accounts inactive >90 days flagged as stale. | Pending |  |  | Medium
💡 HOW TO USE: Select STATUS dropdown → choose Passed / Failed / Skipped. For Failed tests, describe the exact error in the TESTER NOTES column. Date format: DD/MM/YYYY

## 12 ITSM
CyberAssetIQ – Module 12 – ITSM & MSP Integrations
Test Status: Pending ¦ Fill in columns E–H for each test case
TEST ID | TEST NAME | TEST STEPS / HOW TO TEST | EXPECTED RESULT | STATUS | DATE TESTED | TESTER NOTES / BUG DESCRIPTION | PRIORITY
ITSM-01 | Jira Integration – Create Ticket | 1. Navigate to Integrations → ITSM → Jira 2. Configure project key 3. Trigger a High CVE finding 4. Click 'Create Ticket' | Jira ticket created with CVE details, asset name, severity, link back to finding. | Pending |  |  | High
ITSM-02 | ServiceNow Integration | 1. Navigate to Integrations → ITSM → ServiceNow 2. Enter instance URL & credentials 3. Test | Connection successful. Incident can be created from findings. | Pending |  |  | High
ITSM-03 | ConnectWise (MSP) Integration | 1. Navigate to Integrations → MSP → ConnectWise 2. Enter credentials 3. Test | Assets from ConnectWise synced. Tickets can be raised. | Pending |  |  | Medium
ITSM-04 | Datto (MSP) Integration | 1. Navigate to Integrations → MSP → Datto 2. Enter API key 3. Test | Datto endpoints sync to CyberAssetIQ asset inventory. | Pending |  |  | Medium
ITSM-05 | ITSM Ticket Status Sync | 1. Create a ticket from a finding 2. Resolve it in Jira/ServiceNow 3. Check finding status | Finding status updated in CyberAssetIQ when ticket resolved. | Pending |  |  | Medium
💡 HOW TO USE: Select STATUS dropdown → choose Passed / Failed / Skipped. For Failed tests, describe the exact error in the TESTER NOTES column. Date format: DD/MM/YYYY

## 13 Reports
CyberAssetIQ – Module 13 – Reporting & Evidence Packages
Test Status: Pending ¦ Fill in columns E–H for each test case
TEST ID | TEST NAME | TEST STEPS / HOW TO TEST | EXPECTED RESULT | STATUS | DATE TESTED | TESTER NOTES / BUG DESCRIPTION | PRIORITY
RPT-01 | PDF Report Generation | 1. Navigate to Reports 2. Select 'Full Security Report' 3. Click Generate PDF | PDF generated with company branding, all modules summarised, date/time stamp. | Pending |  |  | High
RPT-02 | CE Evidence Package PDF | 1. Navigate to CE module 2. Click 'Generate Evidence Package' 3. Download | PDF contains: asset register, CE control status, evidence for each control. | Pending |  |  | High
RPT-03 | Executive Summary Report | 1. Select Executive Summary report type 2. Generate | Non-technical 1-2 page summary: risk score, key findings, top risks. | Pending |  |  | High
RPT-04 | Vulnerability Report | 1. Select Vulnerability Report 2. Filter by date range 3. Generate | Report lists all CVEs in date range, sorted by severity. | Pending |  |  | Medium
RPT-05 | Scheduled Reports | 1. Set up a scheduled weekly report 2. Wait or manually trigger | Report generated on schedule. Delivered to configured email. | Pending |  |  | Medium
RPT-06 | Report Download (CSV export) | 1. In asset list or vuln list 2. Click Export CSV | CSV file downloaded with all visible data. Correct column headers. | Pending |  |  | Medium
💡 HOW TO USE: Select STATUS dropdown → choose Passed / Failed / Skipped. For Failed tests, describe the exact error in the TESTER NOTES column. Date format: DD/MM/YYYY

## 14 RBAC
CyberAssetIQ – Module 14 – Multi-Tenancy & RBAC
Test Status: Pending ¦ Fill in columns E–H for each test case
TEST ID | TEST NAME | TEST STEPS / HOW TO TEST | EXPECTED RESULT | STATUS | DATE TESTED | TESTER NOTES / BUG DESCRIPTION | PRIORITY
RBAC-01 | Tenant Isolation | 1. Create two tenants 2. Add assets to each 3. Log in as tenant-1 user | Tenant-1 user sees ONLY tenant-1 assets. No cross-tenant data leakage. | Pending |  |  | High
RBAC-02 | Admin vs Read-Only Role | 1. Create a read-only user 2. Log in 3. Attempt to create/delete an asset | Read-only user cannot create, edit, or delete. All buttons greyed out or 403 returned. | Pending |  |  | High
RBAC-03 | API Multi-Tenant Isolation | 1. Use tenant-001 API key 2. Call GET /api/v1/assets 3. Verify no tenant-002 data | API returns only tenant-001 data. Other tenant records not accessible. | Pending |  |  | High
RBAC-04 | New User Invite | 1. Admin invites a new user by email 2. New user receives invite 3. Sets password & logs in | Invite email received. New user onboarded successfully. | Pending |  |  | Medium
💡 HOW TO USE: Select STATUS dropdown → choose Passed / Failed / Skipped. For Failed tests, describe the exact error in the TESTER NOTES column. Date format: DD/MM/YYYY

## 15 Alerts
CyberAssetIQ – Module 15 – Notifications & Alerts
Test Status: Pending ¦ Fill in columns E–H for each test case
TEST ID | TEST NAME | TEST STEPS / HOW TO TEST | EXPECTED RESULT | STATUS | DATE TESTED | TESTER NOTES / BUG DESCRIPTION | PRIORITY
ALERT-01 | Email Alert on Critical CVE | 1. Ensure Gmail SMTP configured 2. Add a Critical CVE to an asset 3. Check email | Email alert received within 5 minutes with CVE details, asset name, severity. | Pending |  |  | High
ALERT-02 | Slack Alert | 1. Configure Slack webhook 2. Trigger a High finding 3. Check Slack channel | Slack message received with finding summary and link. | Pending |  |  | High
ALERT-03 | Dark Web Exposure Alert | 1. Add an email that has a known breach 2. Run check 3. Check notifications | Alert created in notifications panel for dark web match. | Pending |  |  | High
ALERT-04 | Agent Offline Alert | 1. Stop Windows agent 2. Wait for heartbeat timeout 3. Check notifications | Alert generated: 'Agent offline – [hostname]'. Email/Slack sent if configured. | Pending |  |  | Medium
ALERT-05 | Alert Acknowledge & Dismiss | 1. View an active alert 2. Click Acknowledge 3. Check alert status | Alert moved to Acknowledged. No longer in active alerts list. | Pending |  |  | Medium
💡 HOW TO USE: Select STATUS dropdown → choose Passed / Failed / Skipped. For Failed tests, describe the exact error in the TESTER NOTES column. Date format: DD/MM/YYYY

## 16 API
CyberAssetIQ – Module 16 – API Endpoints
Test Status: Pending ¦ Fill in columns E–H for each test case
TEST ID | TEST NAME | TEST STEPS / HOW TO TEST | EXPECTED RESULT | STATUS | DATE TESTED | TESTER NOTES / BUG DESCRIPTION | PRIORITY
API-01 | GET /api/v1/assets | 1. Call GET /api/v1/assets with admin API key 2. Check response | 200 OK. JSON array of assets returned. | Pending |  |  | High
API-02 | POST /api/v1/assets | 1. POST a new asset JSON to /api/v1/assets 2. Check response | 201 Created. New asset in response body. Appears in asset list. | Pending |  |  | High
API-03 | GET /api/v1/vulnerabilities | 1. Call GET /api/v1/vulnerabilities 2. Check response | 200 OK. Vulnerability list returned with CVE IDs, CVSS scores. | Pending |  |  | High
API-04 | GET /api/v1/compliance/ce | 1. Call GET /api/v1/compliance/ce 2. Check response | 200 OK. CE control statuses returned as JSON. | Pending |  |  | High
API-05 | POST /api/v1/scans/trigger | 1. POST to trigger a network scan 2. Check scan starts | 202 Accepted. Scan job queued. Scan ID returned. | Pending |  |  | High
API-06 | Rate Limiting | 1. Send 100+ requests in quick succession 2. Check response after limit | 429 Too Many Requests returned. Rate limit header present. | Pending |  |  | Medium
API-07 | API Documentation (Swagger/OpenAPI) | 1. Navigate to /docs or /api/docs 2. Verify all endpoints listed | Swagger UI loads. All endpoints documented with request/response schemas. | Pending |  |  | Medium
💡 HOW TO USE: Select STATUS dropdown → choose Passed / Failed / Skipped. For Failed tests, describe the exact error in the TESTER NOTES column. Date format: DD/MM/YYYY

## 17 UI
CyberAssetIQ – Module 17 – Dashboard UI & UX
Test Status: Pending ¦ Fill in columns E–H for each test case
TEST ID | TEST NAME | TEST STEPS / HOW TO TEST | EXPECTED RESULT | STATUS | DATE TESTED | TESTER NOTES / BUG DESCRIPTION | PRIORITY
UI-01 | Dashboard Loads After Login | 1. Log in 2. Observe main dashboard | Dashboard renders: asset count, risk score, CVE summary, recent alerts. No blank panels. | Pending |  |  | High
UI-02 | Navigation Menu – All Sections | 1. Click every item in the left-hand menu | Each section loads without 404 or blank page. | Pending |  |  | High
UI-03 | Dark Background – White Text Visibility | 1. Check all headers and panel titles 2. Ensure text is readable | All text on dark backgrounds is WHITE or bright colour. No invisible dark text. | Pending |  |  | High
UI-04 | Mobile / Tablet Responsive | 1. Open on a tablet or use browser dev tools at 768px width | Layout adjusts. No overlapping elements. Navigation accessible. | Pending |  |  | Medium
UI-05 | Loading States | 1. Trigger a slow operation (large scan) 2. Observe UI during load | Loading spinner or progress bar shown. UI does not freeze. | Pending |  |  | Medium
UI-06 | Error Messages | 1. Submit a form with invalid data 2. Disconnect API and attempt action | Clear user-friendly error messages shown. No raw stack traces exposed. | Pending |  |  | High
UI-07 | Ctrl+Shift+R Hard Refresh | 1. Make a backend change 2. Hard refresh browser 3. Verify change reflected | Latest data loads after hard refresh. No cached stale data. | Pending |  |  | Medium
💡 HOW TO USE: Select STATUS dropdown → choose Passed / Failed / Skipped. For Failed tests, describe the exact error in the TESTER NOTES column. Date format: DD/MM/YYYY